## README
Version 1.5, 9 December 2021
What is this document?
This document aims to support you as a researcher to get an overview of the steps you need to carry out for your research. It tells you what steps are possible, why they can or must be taken, and where you can find support
Note, however, that not all steps in this document apply to all research projects and while some steps are mandatory, others are only recommended.
Please also note that this document is by no means exhaustive and we do recommend that you seek specialist advice from experts in case your question is not addressed in this document. If you are not sure whom to ask, please email rdm@vu.nl
What is mandatory and what is recommended?
Basically, anything that is demanded by law is mandatory. This includes anything related to personal data (under the GDPR) and any medical research (under the WMO).
Other steps that are mandatory are demanded by VU Policy, grant providers and/or journals. For example, grant providers usually demand a DMP, and journals sometimes require that you undergo ethical review, even if that is not mandated by law.
Most other steps are only recommended - but with good reason. If steps are recommended, we usually do so because they contribute to Open Science or good research practices, such as transparency and accountability.
How should I use this document?
There is an instructions tab where you can find how to read it and use it for your advantage. This is only the minimum viable product: we hope to be able to offer it to you in a tool, that makes it much more readable and manageable.
What's more, the information in this document will be updated periodically, so this is by no means exhaustive.
Can I contribute to this document?
Yes, by all means, send an email to rdm@vu.nl
What is the RDM Support Desk and how do I reach it?
The RDM Support Desk is located in the University Library and aims to help you with any questions about data management, including solving any technical issues. You can reach it via rdm@vu.nl; it is checked daily by 4 experts working in the University Library.
Where can I find most of the information referenced in this document?
The RDM Handbook is the source of many steps. Find more information on rdm.vu.nl
Who made this document?
This document was created by the Research Support department in the University Library in 2021. They received input from many colleagues: from IT, researchers, and research supporters in faculties.
This all looks very complicated and I don't know how to find anything in this document. Where can I find information instead?
No worries, you can always email rdm@vu.nl and we help you ourselves or refer you to an expert in a different service. Even if you're not sure what to ask us, get in touch!

## Instructions
What is in this document?
This document contains a very big sheet: the research process overview. This aims to give you guidance for many of the steps in your research.
How should I read this document?
Do not panic! Not all steps are applicable to all research projects. This document only tries to spell out what steps could occur. Try to find out what applies to your project and ask for help (rdm@vu.nl) if you are not sure.
Even if you are working with personal data, not all steps for personal data may apply to you, which varies according to the sensitivity of the data with which you're working. Ask advice: rdm@vu.nl
What's more, when you read "PI" or "PhD" you can also read "researcher". What's important is that somebody takes charge of any given steps and this may differ per project
Moreover, where you read "project" you can also read "subproject". Especially at the end of the cycle, when you publish, the same recommendations apply to publishing (the dataset for) a single article as to the project as a whole
Finally, for some projects, the order of the steps may be different and some may take place simultaneously. Try to consider what order is necessary for your research and ask for advice (rdm@vu.nl) if you are not sure
If you are missing some steps that you think are necessary for your project, then by all means, carry out these steps! This document is not yet exhaustive
When should I consult this document?
Ideally, at the very beginning of your research. Some steps occur at the end, but need to be prepared. Make sure that you know, when you prepare the project, what needs to be prepared for when the project ends.
If you are already halfway, no worries, you can also consult this document and, obviously, drop us an email via rdm@vu.nl
Is this the final version of this document?
We hope not! First, we are still working on updating all the information contained here and will keep doing so as policies, regulations, support, tools, and best practices are developing
Second, we hope to be able to transform this document into an interactive tool in the beginning of 2022. We hope it will be easier to use by then
What should I do if I can't find information?
Send an email to rdm@vu.nl and/or consult the RDM Handbook: | rdm.vu.nl

## Research_process_overview
No. | Research Phase | What? | Who (is responsible)? | Where? | Who can assist? | Result | Why? | Notes | Is there a time indication/deadline?
A1 | Before the project starts | Discovering/creating grant opportunities and writing a project proposal | PI | Grant provider | Grants Desk officers and Faculty Grants Advisors can help with identifying possible grants and can assist with the submission process. For some faculties, the Research Office can provide advice on bureacratic procedures such as submission deadlines, institutional hosting agreement, content and structure of the proposal. | Researcher requests project funding | This is a requirement for receiving a grant | Because grant applications take time, it is advisable that you assess your chances of success before starting to write your proposal. Supervisors or grants advisors can help with this.
A2 | Before the project starts | Writing a Data Management paragraph | PI | Grant application | Data steward/RDM Support Desk | A part of the budget is reserved for the data management costs | This is a requirement for receiving a grant | Because the data management has not been worked out yet in the DMP it can be hard to know exactly what costs will be necessary. Data stewards or the RDM Support Desk can help with making a quick estimation based on data volume (storage, archiving), data sensitivity (privacy concerns) and methods (software/hardware needed)
A3 | Before the project starts | Register project funds to Project Control | PI | Project Control | Project Control | Project Control has the project in its administration | This is mandatory for all grants over 25.000 euros | Sometimes even projects under 25.000 euros are better in administration at Projectcontrol. When in doubt contact your project controller. It is necessary to involve project control at the earliest possible stage if you need a project budget for your application. This way they have plenty of time to support you properly. In addition, the internal and external budget for the application must always at least be approved by the director of operations before you can send them to the subsidy provider. This too takes time.
A3 | Before the project starts | In case of a research involiving personal data, get in touch with your privacy champion to assess the feasibility of the project | PI | Privacy Champion | Privacy champion / privacy team legal services (BJZ) | The PI has realistic expectations of the project and its requirements | It saves time later on, the project is feasible, tackling it early on helps the researcher | The actual measures may be taken once the grant proposal has been approved, see steps B8-B13. Click here for more information about privacy in research. | This takes ±2 weeks
A5 | Before the project starts | A discussion with the Dierexperimentencommissie to discuss the involvement of animals in the research (if applicable) | Researcher | AARC | Dierexperimentencommissie (DEC) or Instantie voor Dierenwelzijn (IvD) VU/Vumc. Contact via info.aarc@vu.nl | The researcher complies with the legal requirements around experiments with animals | Legal obligation (Wet op de Dierproeven), see also the website of the Central Committee Animal Testing | At the VU, there is some assistance available to request a licence for doing experiments with animals and to carry out the experiments. See https://vu.nl/nl/medewerker/richtlijnen-en-procedures/dierexperimentencommissie-dec, https://personenzoeker.vu.nl/nl/over-de-vu/profiel-en-missie/uitgelicht/proefdieren/index.aspx and https://personenzoeker.vu.nl/nl/over-de-vu/profiel-en-missie/uitgelicht/proefdieren/dierexperimentencommissie/index.aspx
A6 | Before the project starts | In case of collaborations with research partners (universities, private parties), have a meeting with the Grants Office or the VU legal team, which can help with (review of) legal procedures and documents in cases of public-private collaboration, grants agreements, consortium agreements, etc. | PI | VU Legal | VU legal team: legal@vu.nl | A consortium/collaboration agreement is drafted | In case of consortia and/or collaboration with other universities or private partners
A7 | Before the project starts | Collaboration with IT to discuss any issues and/or costs associated with IT in the project | Researcher | IT for Research or the IT relationship manager for Research | Data steward/RDM Support Desk, to guide the researcher | The researcher has a clear idea of what IT facilities will be necessary, how the research may be adjusted, and what costs may be incurred | Research methods and budgetting may be adapted | The earlier you discuss these matters with IT, the better, especially if you want to budget some of the IT costs from your grant. See also steps B6 and C3-6 | This takes approximately 3 weeks
A8 | Before the project starts | Explore if the research needs to comply with Medical Device Regulations | Researcher | Medical Device Development Expert | MDR Expert | Project complies with MDR legislation | Legal obligation | There is an expert at the Beta faculty who is available for support, also if you need to check if you need to comply with MDR.
A9 | Before the project starts | Explore if an ethics review is necessary; explore if METc review (for medical research) is necessary. Prepare documents for ethics review | Researcher | Faculty ethics committee or METc information page | Secretary or contact person of the review board | Timely preparation of the ethical review | In medical research, METc (Medical-Ethical Review Committee) review is mandated by law, the WMO. For other research, many faculties and journals require an ethics review before you get started/publish your results | As many ethical review procedures require a DMP, the actual submission of the documents usually takes place after the DMP has been finalised, see step C1 | This can take up to 12 weeks. It is recommended to start the process at least 3 months before data collection starts
A10 | Before the project starts | Pre-DPIA (Data Protection Impact Assessment) to check if a full DPIA is necessary (for personal data) | Researcher | Contact your privacy champion for this (https://libguides.vu.nl/ld.php?content_id=32452889) | Privacy champion/lawyer | Clarity if a DPIA is necessary (when a funder does not require it) | Legal obligation (art. 35 of the GDPR) | This may be necessary, as some funders require a DPIA and pre-DPIA. Click here for more information | Although writing a pre-DPIA can, in most cases, be done in under an hour, making an appointment with the VU legal team can take up to two weeks.
B1 | After Grant approval | Get in touch with your grants advisor at the VU Grants Office or in your faculty (if available) | PI | VU Grants Office or the grants advisor in your faculty (if available) | Grants Officer (click here) or the grants advisor in your faculty (if available) | You make sure that all arrangements are made with your grant provider to formally accept the grant and set important dates and agreements for your project | This is required to formally obtain the grant and start your project | Get started with this as soon as you can after hearing about the approval of your application. Depending on your research, a lot may need to happen, many departments at the VU may have to be involved and the time-frame may be very short | This depends on the grant provider's terms, but it be as short as 2 weeks.
B2 | After Grant approval | Inform your project controller about the grant approval to finalize the internal budget | PI | Project controller | Project controller | Your project can be released in SAP so that costs and benefits can be booked. Staff can also be charged on the projects. | Without a released project in SAP you can't run a project because you can't make expenses. | Because there can be a long time between application and award and not everything is always awarded by the subsidy provider, a revised internal budget will be drawn up. The project can only be released once it has been approved by the Director of Operations.
B3 | After Grant approval | Explore if there are any knowledge security issues associated with the project | PI | Advisory group on knowledge security | Advisory group on knowledge security | The researcher is aware of any risks to knowledge security and has taken the necessary steps to mitigate these risks | Partly Dutch and EU legal requirements, also partly VU policy | Knowledge security can play a role in several situations; for example, when you are doing research in an area that could be exploited for nefarious goals ('dual use') or when you work with research partners from certain countries. Click here for more information.
B4 | After Grant approval | Writing a Data Management Plan (DMP) | PhD/PI/Researcher | DMPonline (link here) or another tool of choice | Data steward/RDM Support Desk | A DMP is written and can be submitted | VU Policy | This includes the consultation with expert, and submission with a funder, if applicable. You need to hear back from the funder if it has been accepted. Some funders ask for the DMP after the grant proposal has been approved, others require that you submit the DMP with the grant proposal. Ask your data steward or the RDM Support Desk for help if you are not sure when to submit the DMP. Ethical review committees usually also require a DMP. | Grant providers usually have deadlines for submitting the DMP. For NWO, the procedure is as follows. After approval, researchers have 4 months to write their DMP. The must submit DMP 4 weeks before starting to collect the data.
B5 | After Grant approval | Setting up an administration of project expenses (if the project is not monitored by Project Control) | PI | Ask your data steward or the RDM Support Desk for help | Data Steward/Faculty Research Office/RDM Support Desk | Expenses are traceable | This can be an important tool to uncover fraud/paying for fabricated data and, more generally, helps to keep track of the budget | This requires a redesign of project control procedures; please ask assistance.
B6 | While writing DMP | If applicable, collaboration with IT to discuss the practical set-up of the project (e.g. computing services and environments, security, storage) | PhD/PI/Researcher | IT for Research or the IT relationship manager for Research | Data steward/RDM Support Desk, to guide the researcher | Researcher has everything they need to start the research | The IT setup matches the researcher's needs and legal/policy requirements. This can include going through the Simple Route SaaS (SRS), which is used for connecting external services to VU systems. Researchers need to submit the following documents: 1. A DPIA (step B11); 2. A questionnaire for IT acquisitions; 3. A BIV-classification (CIA-classification, step B10); 4. An SRS checklist | It's important to do this as early as possible (some of this has been prepared in step A7), because depending on the IT services you need, you may need to adapt your research design. For example, if you are planning to use High Performance Computers, you will not be able to use some common tools and will need to come up with something else. The collaboration with IT is continued in steps C3-6
B7 | While writing DMP | Explore what insurance you need, especially if your research falls under the WMO | PI/PhD | Corporate finance | Corporate Finance, Gabriëlle Zegers | The research has an insurance policy | In some cases: legal obligation under the WMO. In other cases: obligation set by the VU. Click here to learn more. | Support is available via your department head or via g.zegers@vu.nl; for all research, especially WMO research, the insurance needs to be taken care of before data collection starts
B8 | While writing DMP | (For research with personal data) Speak to your privacy champion to identify a legal ground for data processing and assess what documents/procedures are necessary, e.g. DPIA, confidentiality statements, informed consent forms, processing agreements, etc. Familiarise yourself with your obligations under the GDPR in research. Explore if pseudonymisation or anonymisation is possible. See also steps B9-13. | PhD/PI/Researcher | Privacy Champion | Privacy champion/lawyer | The researcher is aware of requirements and/or completes a DPIA (see also step B11) | Legal obligation (more information here) | This may be combined with steps B9-13 with the privacy champion
B9 | While writing DMP | (For personal data) Determine partners and suppliers. Complete contracts with partners and/or suppliers. For example, data sharing agreements, data processing agreements, licence agreements, joint controller agreements, consortium agreements, etc. | PhD/PI/Researcher | Several services are offered depending on the type of contract needed | IXA (info@ixa.nl) Legal affairs, privacy champion, privacy lawyer, grants desk | Contracts are signed | Depending on the type of research and necessary contract: legal obligation (e.g. art. 26 GDPR); requirement for grants; determining intellectual property or the legal position of the VU; required by the insurance provider | For anything concerning privacy, privacy champions/lawyers should be consulted. Click here to be referred to the page on our LibGuide.
B10 | While writing DMP | Complete a Data classification | PhD/PI/Researcher | Classification tool | Data steward/RDM Support Desk | Researcher knows how their data classify | It is helpful for completing a BIV, writing a DPIA (step B11) and determining security criteria (steps C3-6) | The Data Classification is a first step; if it turns out a full BIV classification is needed, please get in touch with rdm@vu.nl
B11 | While writing DMP | (For personal data) Complete a DPIA (Data Protection Impact Assessment) in case a funder demands it or the Pre-DPIA advised it | PhD/PI/Researcher | Word template | Privacy champion/lawyer | Privacy risks are mitigated | Legal obligation (art. 35 of the GDPR) | The privacy champion is the first point of contact here.
B12 | While writing DMP | (For personal data) Draft informed consent forms | PhD/PI/Researcher |  | Privacy champion | The researcher has informed consent forms for the participants to sign | Legal obligation (art. 6 and 7 of the GDPR), ethical obligation
B13 | While writing DMP | (For personal data) Complete a privacy statement and make it available (and findable) for research subjects | PhD/PI/Researcher | A template is available from your privacy champion | Privacy champion | The researcher has a privacy statement for participants to read. | Legal obligation (art. 13 or 14 of the GDPR) | Privacy champions have a template
B14 | While writing DMP | Comply with the requirements of the Nagoya Protocol (when working with imported or exported organic/genetic materials) | PhD/PI/Researcher | https://vu.nl/nl/medewerker/beta-wegwijzer/nagoya-protocol-beta | The Nagoya Protocol Support at Beta; nagoya@vu.nl | Compliance with Nagoya Protocol | Legal obligation | Beta has a step-by-step guide available, click here
C1 | After writing DMP | Ethical review | PhD/PI/Researcher | METc or Ethical review committee | Secretary or contact person of the Review Board | Researcher gets the permissions they need. | Legal obligation (https://english.ccmo.nl/mrecs) for medical research and/or VU/faculty/journal policy for other fields | This follows the preparation done in step A9. For WMO research, you also need to sign up for the WMO insurance. | This can take up to 3 months and ethical approval has to be obtained before starting the data collection
C2 | After writing DMP | For WMO research: sign up for the proefpersonenverzekering (insurance for test subjects) and the liability insurance | PhD/PI/Researcher | Corporate finance | Corporate Finance, Gabriëlle Zegers | Researcher is insured against harm in test subjects | Legal obligation under the WMO (click here)
C3 | After writing DMP | Perform the risk analysis, which is necessary for research processing sensitive data using unclassified IT tools | PhD/PI/Researcher | IT Security & Privacy | Data steward/RDM Support Desk, to guide the researcher | It is clear how tools must be used and data must be handled | To ensure the security of the research and the data management | The earlier this is done, the better. This can take place simultaneously with steps B6 and C4-6. | This depends on a number of factors, among which whether you already have documentation such as a CIA classification (step B10), a DMP (step B4) and other documentation such as processing agreements (step B9), if applicable
C4 | After writing DMP | If mandated by steps B6 and C3, design a security plan, which is an outcome of the risk analysis and serves as the guideline for implementing the IT services | PhD/PI/Researcher | IT Security & Privacy | Data steward/RDM Support Desk, to guide the researcher | The IT services can be implemented | To ensure the security of the research and the data management | The earlier this is done, the better. This can take place simultaneously with steps B6, C3, C5-6. | This depends on a number of factors, among which whether you already have documentation such as a CIA classification (step B10), a DMP (step B4) and other documentation such as processing agreements (step B9), if applicable
C5 | After writing DMP | Set up the technical environment based on the security plan (step C4) or the researcher's needs | PhD/PI/Researcher | IT for Research | IT for Research or the relationship manager of the Research domain in IT | A technical environment is ready for use | To equip the researcher with the necessary software/hardware to do the research | The earlier this is done, the better. This can take place simultaneously with steps B6 and C3-4. | This depends on the services required
C6 | After writing DMP | Select and apply for a Storage Environment | PhD/PI/Researcher | Network RDS | Data steward/RDM Support Desk/IT for Research | The researcher has access to Research Drove, a project folder on G/Sharepoint, iRODs/Yoda or OSF | This is necessary for these forms of storage. For some other forms of storage (OneDrive, Teams), a researcher has access automatically. More info: click here
C7 | After writing DMP | IT Security & Privacy give input for Annex 3 of a processing agreement. They can use the results of steps C3-5 as input | PhD/PI/Researcher | IT Security & Privacy | Data steward/RDM Support Desk, to guide the researcher | The processing agreement is completed (see step B9) | Legal obligation (as part of the GDPR) | This usually happens after talking to the privacy champion in step B8.
C8 | After writing DMP | Set up a repository and a robust version control system for the research software | PhD/PI/Researcher | This can be done in the software and applications that are being used | Data manager/data steward/RDM Support Desk | A version control system is in place, resulting in the possibility for others to contribute and for the researcher to check collection/processing/analysis steps and repair mistakes | This contributes to Open Science, but also to (data) quality assurance. It will help you to enhance transparency and reproducibility, and increase the likelyhood of catching mistakes | What this looks like differs per discipline and methodology. We strongly recommend that you seek advice from your data steward. We also recommend that you use tools that have version control built in (e.g. git, Research Drive, Yoda). Click here for more information about repositories and version control
C9 | After writing DMP | Preregister the study | PhD/PI/Researcher | OSF (offered by VU) or AsPredicted | Data steward/RDM Support Desk | The study is pre-registered | This contributes to research transparency and helps you to ward off allegations of fraud | Although preregistrering a hypothesis can be done much earlier, in the research proposal stage, registering the (pre)processing and analysis steps is usually done at this stage
C10 | After writing DMP | If you are working with personal data, register your research data in the processing register (= a register that keeps track of all research projects that process personal data) | PhD/PI/Researcher | DMPonline (link here). The GDPR registration can also be completed as part of the DMP (step B4) | Privacy champion | The research is entered into the processing register | Legal obligation (art. 30 of the GDPR) and VU policy | Instructions on how to complete the GDPR registration are here | After completing a privacy statement (step B13) this should not be more than 10 minutes of work.
D1 | During the project: data collection | Report to project control about significant changes concerning the project (budget, duration, staffing, etc.) | PI | Project controller | Project controller | An up to date budget that complies with the subsidy rules | Changes to a research project must almost always be reported to the grant provider in good time. Failure to do so may result in costs being rejected. | The project controller will also contact you at least twice a year to discuss all project finances with you.
D2 | During the project: data collection | Prepare data for compliance with the FAIR principles and the GDPR, if applicable | Researcher | In storage location | Data steward/RDM Support Desk | Data are FAIR, or in case of personal data: pseudonymous/anonymous | VU and VSNU policy / legal obligation (GDPR), if working with personal data | This consists of multiple steps, e.g. designing a data collection protocol, creating a file and folder system that work well, deciding on metadata and ontologies to use, choosing a repository that is suitable for the data and the discipline. If you are working with personal data, any decision about pseudo-/anonymisation and data sharing or making data available after the project needs to be considered when you create the informed consent form (see step B12)
E1 | During the project: data storage and sharing | Storing and sharing research data with research partners | Researcher/PI | Storage location (selected in step C6, click here to go to our LibGuide) | Data steward/RDM Support Desk | Data are stored and shared in a structured, traceable and documented manner, and are secured and protected according to their sensitivity. | It is good practice to store and share your data in a structured, traceable and documented manner. It also enhances research transparency, reduces the chance of making mistakes and increases the likelihood to catch them, and a file versioning system enables you as a researcher to go back to a previous version if necessary. | Some guidance is available through the CESSDA: https://www.cessda.eu/Training/Training-Resources/Library/Data-Management-Expert-Guide/2.-Organise-Document/Designing-a-data-file-structure. See also step C8 for setting up version control.
F1 | During the project: data analysis | Document data processing and analysis steps | Researcher | In storage location/analysis software/hardware | Data manager/data steward/RDM Support Desk | Data are FAIR | VU and VSNU Policy, this is good for the transparency and reproducibility of your research | This could take various forms, e.g. a codebook, a logbook, a lab notebook, a data list, a readme file, and comments in code and syntax. Click here to go to the LibGuide.
F2 | During the project: data analysis | For some projects: write and document code/scripts | Researcher | In a notebook application such as Jupyter Notebook, R Studio, or a tool such as MATLAB or SPSS | Data steward, colleague, data manager, research software engineer | You document what your code does, why it does that, and how it does that | This is good scientific practice, enhances your research transparency and reproducibility and helps you to catch mistakes | This is part of your data and research documentation. Part of this can also be a a software checklist (click here). See also step F1.
G1 | At the end of the project | Publish pre-print (if desired) | PI/PhD/Researcher | A preprint server that is customary in your field | Data Steward/Research Support Officer/departmental guidelines | A preprint is published so that the results of the research are accessible to anybody | This contributes to Open Science. In principle, it is not mandatory to publish a preprint, although some departmental guidelines may encourage you to do so. Discuss this with your head of department if you need guidance for publishing a preprint. | You can also get feedback from peers on your preprint, on the basis of which you can update the preprint before you submit it to a journal. It is up to you when you want to start sharing your outcomes (in such a preprint), this can also be done quite early in the research process, if you like. Discuss this with a supervisor or a department head.
G2 | At the end of the project | Contact your project controller to discuss together how you can bring the financial completion of the project to a succesful conclusion | PI | Project controller | Project controller | A financial final report that is submitted on time | Failure to submit the final financial report or not to submit it on time may lead to less subsidy being obtained. | Projectcontrol works with checklists on every project. The projectcontroller wil contact you at least 4 weeks before reaching the project end date to discuss the entire process of final accountability together. | Project control will contact you 4 weeks before the end date of the project
G3 | At the end of the project | Produce an "Access policy": determine who gets access and who grants access (and how) | PI | Department or faculty | Data steward/RDM Support Desk | An access policy is in place, it is clear who is responsible for the data management | This contributes to FAIR, because it creates clarity about the accessibility of your data and software | This should be prepared before the project ends, ideally as part of the DMP (step B4) and discussed with a department head, data steward or policy officer. If you are working with personal data, you need to think about who will be granted access when you create your informed consent form (see step B12)
G4 | At the end of the project | Credit your contributors | Researcher | As part of the publication, in the metadata of the data repository, in the documentation | Data steward/RDM Support Desk | All contributors receive appropriate credit | This is good academic practice and contributes to Open Science (e.g. if you received help from a data manager or librarian who performed a systematic review for you) | You can use the CREDIT taxonomy for this task (click here). This is important for all phases of your research, but especially once you start publishing.
G5 | At the end of the project | Consider how FAIR your data and software are and/or how to make them more FAIR. Convert your files to preferred formats. | Researcher | Recommendations for FAIR data can be found here: https://fairaware.dans.knaw.nl/ and for FAIR software here: https://fair-software.nl/. More information about preferred formats: https://dans.knaw.nl/en/about/services/easy/information-about-depositing-data/before-depositing/file-formats?set_language=en | Data steward/RDM Support Desk | The data and software are FAIR | The VU endorses FAIR data and software | FAIRification has to be planned before the project starts and carried out during data collection and analysis, but at the end of the project, certain measures can still be taken to FAIRify your data further, e.g. by registering the dataset in PURE (step G9), by making syntax available and by using preferred formats to save your data (see also step G8).
G6 | At the end of the project | Decide on a licence for your dataset and your software - a licence dictates what others may do with your data/software and how they may be reused or remixed. Separate licences should be applied to data and software | Researcher | More information for data and software licences is here | Data steward/RDM Support Desk | The data and software have licences | This is good practice, good (Open) science and enables others to reuse your work properly | More information for data licences is here: https://libguides.vu.nl/rdm/data-publication?#s-lg-box-wrapper-15125678 and for software licences is here: https://fair-software.nl/recommendations/license
G7 | At the end of the project | Make sure that your software is citable | Researcher | Add a CITATION.cff file to your software | Research Software Engineer/Data Steward/RDM Support Desk | You and others can cite the software | This helps you to get credit and recognition for the software you wrote | This goes hand in hand with the preservation of the software. Make sure that your CITATION.cff file is also part of the archived/published software package (see step G8)
G8 | At the end of the project | Submit all dataset(s) and/or (replication) code, syntax and/or software written by the researcher. (Sometimes as a publication package) | PI/PhD/researcher, sometimes a data manager | Data archive or repository; data journal | Data Steward, RDM Support Desk or functional management (if a VU tool is used). More information is also on the LibGuide | FAIR data and verifiable publications | VU RDM Policy | Ideally, this is planned in advance and researchers are aware what data can be published and what data need to be archived securely. Creating and submitting a publication package must be done for every publication you make, also when it is part of a project and not yet the end of it.
G9 | At the end of the project | Register dataset(s) | PhD/PI/Researcher | PURE | PURE functional manager, a manual is on the RDM Handbook | Data are FINDABLE | VU RDM Policy | Metadata of the project are shared, support can be provided by a Data Steward or the RDM Support Desk
G10 | At the end of the project | Register software | PhD/PI/Researcher | In PURE | Data steward/RDM Support Desk/Research Software Engineer | Software is findable | This helps you to make your research output more visible and can result in your software being reused | If you like, you can also register your software in a community registry.
G11 | At the end of the project | Depending on the level of accessibility of the data and how/where they are archived an published, you need to give access to others and/or maintain the data | The person responsible for the data (see also "access policy", step G3) | Data archive or repository | Department head/data manager or steward, functional manager of tool used | Data are FAIR | VU RDM Policy | This facilitates reuse of the dataset by the same researchers or providing access and reuse to others
G12 | At the end of the project | For personal data: handle questions and/or requests from data subjects, handle personal data breaches | The person responsible for the data (see also "access policy", step G3) | VU Data Protection Officer | VU Data Protection Officer | Legal obligations are met (several articles of the GDPR) | Legal obligation (several articles of the GDPR) and VU RDM Policy | This can occur at any time in the project, but is specified here to emphasise that you need to have a plan in place, should this happen after the project has ended. The VU Data Protection Officer can assist here. Any data breaches need to be reported to the IT Servicedesk immediately: servicedesk.it@vu.nl
G13 | At the end of the project | Prepare communication about your research | PI/PhD | University/faculty website, (national) media, social media/etc. | Faculty communications office | The research outcomes are disseminated | This increases research impact and contributes to further research | This should be planned carefully and in cooperation with faculty/university communications officers.

## Versions
Version | Date | Updated by | Remarks
1.5 | 2021_12_09 | Elisa (UB) | First published version
1.5.1 | 2023_04_17 | Elisa (UB) | Remarks by several colleagues, small updates because of situation changes
1.5.2 | 2023_07_19 | Elisa (UB) | Instructions about software management added
1.5.2.1 | 2025_03_20 | Elisa (UB) | Changed LibGuide references to RDM Handbook